2026 Event Management Plan

Event Plan Template

| Name of event |  | Coastal Twist Fair Day 2026 |
| --- | --- | --- |
| Dates of event |  | The proposal is for a single day event (Coastal Twist) on an ongoing basis each year on the 1st of October (this will ensure we can run the event, any day of the month of October) . |
| Time of event |  | Bump-in 0600 – 1000hrs Temporary market event 1000 – 1700hrs Bump-out 1700 – 2000hrs |
| Location of event |  | Peninsula Recreation Precinct, Sydney Avenue Umina Beach |
| Event coordinator/contact person |  | Festival Director: Glitta Supernova Operations Managing Director: Juan Iocco Logistics, Governance: Jess Mcleod Volunteer coordinator: Kirsty Cartan |
| Target audience |  | 30% tourists and 70% locals |
| Expected attendees |  | Up to 2,000 people (weather dependant) - Intense council blockers across 2 years have damaged festival ability to promote, go live and gain timely approvals and cohesive approach, we are working to rebuild with support from STATE including around new vibrancy and special events management rules being introduced |
| Objectives – why |  | - A happier healthier and more welcoming central coast - Cohesion to a region previously known for its lack of authentic Diversity and Inclusion - Bring vibrancy and visible diversity to the region. - Promote participation and active engagement of arts and culture based activities which strengthen the cultural fabric of our Central Coast community. - Promote and grow tourism that celebrates both the natural and the cultural human assets of the Central Coast in a way that is accessible and sustainable. - Pushing forward with - brighter: perceptions (of the region), - possibilities (for the region) and - equity (in the region). - Push for innovative original programming that challenges current cultural ways - Visibility and space in a region where this is not always possible. |
| Description of event | Coastal Twist 2026 fair day is a celebration of voice and inclusion on central coast nsw, now a annual pilgrimage which extends long weekend stays, ignites live arts and culture and gives voice to our community as a diverse, vibrant and active one, The days plays hosts to community and artisan stlls, live dance, music, dog parade, food stall/vans and partnering with up to 100 local and national organisations and businesses |  |
| Event participation - Please outline how you intend to measure attendance at your event? Measuring crowds and visitor participation is essential in understanding the return economic value of an event and calculates its return on investment to local area. Crowd counting or crowd estimating is a technique used to count or estimate the number of people in a crowd. The most direct method is to count or tally each person in the crowd upon arrival. Another method involves dividing the area occupied by a crowd into sections, determining an average number of people in each section, and multiplying by the number of sections occupied. | Free/Non Ticketed events - Crowd counting / Drones/ photos - crowd densities (open access methodology) - economic impact assessment - Attendee satisfaction - Social Media engagement |  |

| Please outline the management structure of your event organisation including the key roles and responsibilities and the use of unpaid/paid staff? | Festival Director Glitta Supernova, 80% Volunteer 20% Paid Juan Iocco (Logistics, Safety)– Volunteer Jess Mclead – Operations - Volunteer 5 Leads: Volunteer - Rainbow families + Youth Lead - Stall holders + community groups Lead - Branding, Marketing, Media Manager - Digital Manager - Volunteers Lead Volunteer Team – Crowd counting, Support, Surveys, incident reporting |
| --- | --- |
| Wet Weather – please identify your wet weather contingency plan? Outdoor events always come with a chance of rain, thunderstorms, wind or extreme heat. No matter what the size of your event, you will always need to establish an extreme weather contingency plan. To ensure nothing is left to chance, start the conversations early in your planning phase and include your contingency plan costs in your event budget. Leaving things to chance and hoping that your event isn’t a wash out will not keep punters on event day and WILL impact your events’ profitability. | Fair Day is an outdoor all weather event. we will clearly advertise: “Rather than bringing an umbrella with you, we suggest bringing a disposable poncho in the event of wet weather” |

Early Event Planning Template

| Early event planning | Person responsible | Action | Date to be completed |
| --- | --- | --- | --- |
| Budget - Source identified - Sponsorship | Juan | Currently working on grants and private sponsorship | May 2026 |
| Ticketed event? - Finalise costs of event - Create website ticketing system | Melissa | build website with accessible ticketing and inclusion of “experiences” (local small business offerings) | May 2026 |
| Experiences / Partnering - Corporate, Gov and Global business owners - All Coastie business owners | All leads | Engage businesses across the peninsula to support the event and for inclusion in our “experiences” Eg: restaurants offering discounts, Surf school doing lessons, Aboriginal tour, Kayaking | Dec 2025 – July 2026 |

| Event Hub Advertising - Posters/Flyers - Social Media - Local Media and Sponsors - Mardi Gras / Pride Alliance - Website | Glitta / Melissa | Create Build momentum Share amongst networks Engage LGBTIQ Sydney editors | June – Sep 2026 |
| --- | --- | --- | --- |
| Talent / Entertainment | Glitta | Currently locking in talent and curating events | Jan – June 2026 |
| Signage | Juan | Conversations ongoing with RMS/RFS/Brisbane water Police/SES | June 2026 |
| Program/running sheet | Glitta /Volunteers | Lock in events Lock in artists Lock in venues Lock, train, engage volunteers | Mar – Sep 2026 |
| - Running sheet written |  |  |  |
| - Program/running sheet sent to staff/volunteers |  |  |  |
| - Staff/volunteers fully briefed |  |  |  |
| Tech requirements - PA system - backline | Tim Audio Visual Tech | Connect with all artists for requirements | Mar – Sep 2026 |
| - microphones |  | Connect with all |  |
| - Lighting |  | venues for access |  |
| - Extra electrical requirements |  | and power |  |
| - Marques - Staging |  | Lock in specs with Bax audio visual Confirm outdoor |  |
|  |  | events with Surf |  |
|  |  | club and council |  |
| Staffing | Volunteer lead | Brief teams Brief stall holders | Apr -Oct 2026 |
| Ambience - Can the theme of the event be followed in decorations? - Background music needed? | Colin/Glitta | BYO stalls by community groups or supply |  |
|  |  | Continue laisse with council |  |
| Guest comfort / Abilities - Wheelchair access - Accessibility - Toilet facilities | Lead 2 | Continue working with Ability links to ensure all events and venue are accessible | Ongoing |
| - Waste and bins |  | Council – confirm extra bin booking |  |

|  |  | Toilet hire requirement booking |  |
| --- | --- | --- | --- |
| Housekeeping - Cleaning before and after - On standby during the event | All Leads | Currently creating roster | June 2026 |
| Car Parking / Traffic Management - Allocate space for parking for staff/volunteers - Finalise guest car parking onsite – ensure correct permissions are in place - Car parking marshals and signage for event day | Lead 1 | Conversations and sign offs with : DART Brisbane water Police SES | Mar – Sep 2026 |
| On the day - Time for set up by whom - Time for dismantle by whom - Stage | Lead 1/ Creative Director /Stage Manager/ Youth lead | Ensure all stall holder’s setup to site plan. Staging setup | Oct 3 2026 |
| - Tables, chairs layout |  |  |  |
| - Floor plan - Visitor Tally |  | family setup |  |
|  |  | Ensure area is left as found |  |
|  |  | rentals to remove audio |  |
|  |  | Stall holders cleared |  |